Department of Computer Science

Introduction to Software Engineering (COSC 336)

PHASE 2

Feasibility Study

Intelligent, AI-Powered Circular Campus Resource Exchange

and Asset Life Cycle Management System

# Phase 2: Feasibility Document

| Item | Details |
| --- | --- |
| Prepared by | Maryam Alshehhi - 100066369 Ghala Alabdouli - 100064621 Maitha Almaeeni - 100066275 |
| Group / Section | [Group 9 / Lab Section : B2] |
| Prepared for | Khalifa University - COSC 336 |
| Date | 22 September 2026 |

# Table of Contents

4. Financial and Schedule Feasibility
4.1 Purpose and Assigned Scope
4.2 Basis, Assumptions, and Limits

5. Financial Feasibility
5.1 Financial Approach
5.2 Prototype Cost Plan
5.3 AI/API Expense Control
5.4 Maintenance Cost

6. Cost-Benefit Analysis
6.1 Expected Benefits
6.2 Measurement Framework
6.3 Cost-Benefit Assessment

7. Schedule Feasibility
7.1 Semester Schedule
7.2 Team Availability and Workload
7.3 Milestones and Dependencies

8. Resource Plan

9. Financial and Schedule Risk Analysis

10. Feasibility Finding

11. Operational Feasibility
11.1 Stakeholder Adoption
11.2 Workflows
11.3 Training
11.4 Role Permissions

12. Legal and Ethical Feasibility
12.1 Privacy and Security
12.2 Asset Ownership
12.3 Procurement Rules
12.4 Safety
12.5 Responsible AI
12.6 Human Approval

13. Stakeholder Impact

14. Policy Risks and Mitigation

15. References

- Financial and Schedule Feasibility

4.1 Purpose and Assigned Scope

The assigned area is financial and schedule feasibility: development and infrastructure costs, AI/API expenses, maintenance costs, potential savings from avoided purchases, team availability, milestones, dependencies, and semester constraints. The required outputs are a cost-benefit analysis, schedule, resource plan, and financial/schedule risk analysis [14].

The official project description requires Phase 2 to assess financial feasibility, schedule feasibility, and the availability of technical resources across the semester [11]. The analysis below, therefore focuses on whether the proposed academic prototype can be completed at a reasonable incremental cost and within the Fall 2026 course schedule. It does not replace the final team-wide go / conditional go / no-go recommendation, which the three members are expected to prepare jointly [14].

4.2 Basis, Assumptions, and Limits

The analysis uses the scope and assumptions already established in Phase 1. The project is an academic prototype rather than a university-wide production deployment; direct integration with real finance/ERP systems is outside the current scope. Phase 1 also allows sample or synthetic data if real university data is unavailable and keeps final high-impact decisions under authorized human control [12].

No confirmed Khalifa University procurement prices, cloud quotations, AI vendor contract rates, or team labor rates were provided in the project materials. Therefore, monetary figures in this document are planning estimates for feasibility analysis, not quotations or claims about actual university costs. Before the combined Phase 2 submission is finalized, the team should replace any estimate that becomes known with an actual price or approved course assumption.

- Financial Feasibility

5.1 Financial Approach

The prototype is financially feasible only if it is kept deliberately lightweight. The Phase 1 scope already avoids production-scale deployment, hardware tracking, and direct enterprise-system integration [12]. That boundary reduces the need for paid infrastructure and permits the team to develop on existing laptops/lab machines, use open-source software where practical, and run a small demonstration environment rather than a permanent production service.

Git and GitHub are already required for the project. The course onboarding guide states that eligible students can apply for the GitHub Student Developer Pack and receive the Copilot Student plan; this can reduce the direct cash cost of development tooling if the team is approved [13]. Because eligibility and quotas can vary, the financial plan does not depend on paid Copilot or any single commercial AI service.

5.2 Prototype Cost Plan

The Table gives a conservative planning budget for the academic prototype. The ranges are intentionally broad because Member 1 will finalize the architecture and selected services. The team should treat the upper values as control limits rather than targets.

| Cost category | Planned approach | Estimated incremental cash cost (AED) | Cost-control rule |
| --- | --- | --- | --- |
| Development tools and source control | Use Git/GitHub, university/personal IDEs, and open-source libraries where practical. | 0-100 | Do not purchase a tool if a free/student option meets the prototype need. |
| Developer hardware | Use existing personal or university computers. | 0 | No new hardware is required for the prototype scope. |
| Database and application hosting | Develop locally first; use a small free/low-cost test deployment only if needed for demonstration. | 0-200 | Keep one small environment; remove unused services after testing. |
| AI/API usage | Use small test sets, caching, limited prompts/calls, and local/free alternatives where practical. | 0-300 | Set usage limits and review consumption weekly. |
| Storage and backup | Use repository storage plus small sample/synthetic datasets and basic backups. | 0-50 | Do not store unnecessary large files or sensitive datasets. |
| Contingency reserve | Reserve for an unexpected paid dependency, quota overrun, or short demo requirement. | 0-100 | Spend only after team review. |

Under this plan, the expected direct cash cost can remain close to AED 0 if free/student resources are sufficient. A cautious planning ceiling is approximately AED 650 for the semester, including contingency. This ceiling is a feasibility assumption created for this analysis, not a course requirement. Any service choice that would push the prototype materially above this level should trigger a design review and a search for a lower-cost alternative.

5.3 AI/API Expense Control

AI services are the most uncertain variable because the final model/provider has not yet been selected. The project requires AI-enhanced functions such as classification, semantic matching, recommendation explanations, an LLM assistant, and AI-generated reporting [11]. To keep these features financially feasible, the team should separate demonstration quality from production scale.

• Use a small, documented test dataset rather than high-volume live traffic.

• Cache repeated test outputs and avoid rerunning identical prompts or embeddings.

• Set a per-week API spending/usage limit and review it before larger experiments.

• Prefer low-cost/local methods for deterministic functions and reserve external AI calls for features where they add clear value.

• Keep a simple fallback so the prototype can still be demonstrated if a paid API quota is exhausted or a service becomes unavailable.

5.4 Maintenance Cost

During the semester, most maintenance cost is expected to be team effort rather than cash expenditure. Typical work includes fixing defects, updating dependencies, maintaining sample data, adjusting integration code, monitoring API usage, resolving merge conflicts, and keeping documentation synchronized with the implementation. This effort must be scheduled even when the direct monetary cost is low.

Long-term university production maintenance is outside the current Phase 1 scope [12]. A real deployment would require a separate budget for hosting, backups, security monitoring, identity integration, support, data governance, service-level expectations, and possible ongoing AI/API fees. The current prototype should therefore demonstrate maintainability without claiming that its semester budget represents a production operating cost.

- Cost-Benefit Analysis

6.1 Expected Benefits

The financial benefit of the proposed system comes primarily from enabling reuse before new purchasing. The project description explicitly identifies avoided purchases and financial savings as outcomes the system should measure [11]. Other benefits - such as reduced waste, improved asset visibility, better maintenance history, and faster matching - are valuable, but they should not be converted into monetary savings unless the team has evidence for the conversion.

6.2 Measurement Framework

Because real procurement data is not yet available, the Phase 2 analysis should use a transparent calculation framework rather than inventing university savings. The following formulas can be applied later to real or approved sample data:

• Gross avoided-purchase value = sum of the estimated new-purchase prices of assets that are successfully reused instead of purchased.

• Net reuse saving = avoided-purchase value - transfer cost - inspection cost - repair/refurbishment cost - other handling cost.

• Overall net financial benefit = total net reuse saving - incremental prototype/operating cash cost.

• Break-even number of successful reuses = incremental system cash cost / average net saving per reused asset.

For example, if a reused item avoids a hypothetical AED 1,000 purchase and requires AED 150 in transfer/repair/handling, the net reuse saving for that item would be AED 850. If the prototype incurred AED 300 of incremental cash cost, one such reuse would more than cover that cash cost. This example is illustrative only and is not a claim about actual Khalifa University procurement prices.

6.3 Cost-Benefit Assessment Schedule Feasibility

| Area | Benefit / cost effect | Member 2 assessment |
| --- | --- | --- |
| Direct development cost | Can be kept low by using existing devices, open-source/student tools, local development, and controlled API use. | Favorable for an academic prototype. |
| Avoided purchases | A successful internal reuse can avoid or reduce the need for a new purchase, subject to transfer/repair costs. | Potentially high benefit; must be measured with real/approved data. |
| Maintenance and support | Semester maintenance is mainly team effort; production support would create recurring costs. | Manageable for prototype; production cost not yet established. |
| AI/API cost | Variable and provider-dependent. Cost rises with usage volume and repeated experimentation. | Manageable if usage caps and fallbacks are enforced. |
| Financial evidence quality | Actual procurement, transfer, repair, and operating data are not yet confirmed. | Current conclusion is conditional on validating assumptions later. |

- Schedule Feasibility

7.1 Semester Schedule

The Phase 1 document follows the lab schedule in which Phase 2 is due in the week of 21 September 2026, Phase 3 in the week of 5 October, Phases 4 and 5 in the week of 26 October, Phase 6 in the week of 16 November, and Phases 7 and 8 in the week of 23 November [12]. This creates a short, sequential semester plan with increasing integration pressure near the end.

| Milestone | Timing | Member 2 schedule focus | Main dependency | Schedule implication |
| --- | --- | --- | --- | --- |
| Phase 2 - Feasibility | Week of Sep 21 | Complete cost-benefit, schedule, resource plan, and risks. | Shared scope/assumptions and inputs from Members 1 and 3. | Must be finished quickly and leave clear assumptions for later phases. |
| Phase 3 - Requirements | Week of Oct 5 | Update cost/schedule assumptions if requirements expand or shrink. | Stable prioritized requirements. | Scope growth after this point should be controlled. |
| Phases 4 & 5 - Design | Week of Oct 26 | Confirm selected stack fits budget and implementation time. | Architecture, database, interface, AI design. | Late stack changes would create rework. |
| Phase 6 - Development | Week of Nov 16 | Track progress against major-feature milestone; monitor API/hosting usage. | Integrated code and data model. | Major features must be demonstrable before final testing week. |
| Phases 7 & 8 - Test/Final | Week of Nov 23 | Protect time for testing, fixes, presentation, and final integration. | Stable integrated prototype. | High risk of compression because testing and final submission occur in the same week. |

7.2 Team Availability and Workload

The Phase 2 work-allocation guidance assumes three members, each owning a different analytical area and jointly completing shared scope/assumptions, the risk register, classic-versus-AI comparison, final recommendation, editing, references, and submission review [14]. Schedule feasibility therefore depends on parallel work rather than one member completing the entire phase sequentially.

For the remainder of the semester, the safest planning assumption is that each member has limited weekly availability because the project runs alongside other coursework. The team should plan work in small tasks, integrate frequently, and finish required Must-Have features before optional extensions. This is consistent with the Phase 1 hybrid method, which combines fixed phase submissions with short Agile-style tasks, regular reviews, early testing, and frequent integration [12].

7.3 Milestones and Dependencies

| Dependency | Needed by | Risk if late | Control |
| --- | --- | --- | --- |
| Final architecture/technology choices from Member 1 | Early design phase | Budget estimates and implementation plan remain uncertain. | Freeze a minimum viable stack before detailed design; changes require team review. |
| Operational/legal constraints from Member 3 | Before design decisions are locked | A technically cheap solution may violate privacy, policy, or approval needs. | Review constraints before committing to external data/services. |
| Prioritized requirements | Phase 3 / start of design | Scope expansion consumes time and API/hosting budget. | Use Must/Should/Could priorities and defer optional features. |
| Sample/synthetic dataset | Before AI integration and testing | AI matching/classification cannot be tested consistently. | Create a small documented dataset early if real data is unavailable. |
| Integrated baseline workflows | Before Phase 6 deadline | AI features cannot be demonstrated in context. | Integrate core asset/request/transfer flows before polishing optional AI features. |
| Stable build for testing | Before week of Nov 23 | Testing, fixes, report, and presentation collide. | Set an internal code-freeze several days before the lab deadline. |

- Resource Plan

The resource plan below is intentionally high-level because the exact architecture belongs to Member 1. Its purpose is to show that the team has sufficient people, tools, data, and time to complete the prototype without assuming production-scale resources.

| Resource | Planned availability / use | Cost / capacity assumption | Management action |
| --- | --- | --- | --- |
| Three team members | Parallel ownership of technical/AI, financial/schedule, and operational/legal analysis; shared integration and final recommendation. | Main constraint is time, not salary cost for the course prototype. | Assign clear owners, peer-review sections, and use internal deadlines before lab submission. |
| Development computers | Existing personal or university devices. | No planned new hardware purchase. | Keep prototype requirements within ordinary student-computer capability. |
| Git/GitHub repository | Required project repository with individual accounts, branches, commits, and pull-request review. | Expected low/no direct cash cost for student use. | Commit regularly and avoid last-minute bulk integration. |
| Database / hosting | Local development first; small demo deployment only if required. | Use free/low-cost capacity and stay within the planning ceiling. | Monitor usage; remove inactive resources. |
| AI service / local model | Small-scale classification, matching, explanation, assistant, or reporting experiments. | Usage must remain capped because final provider/cost is not fixed. | Track calls/cost; use fallback/local options where appropriate. |
| Project data | Sample/synthetic data unless approved real/anonymized data becomes available. | Small dataset is sufficient for prototype demonstration. | Document source, assumptions, quality limits, and privacy treatment. |
| Collaboration time | Weekly integration/review plus extra time before phase deadlines. | Schedule buffer is limited near final testing/submission. | Use short tasks, frequent merges, and an internal code-freeze. |

For clear contribution records, the Phase 2 guidance requires separate branches, regular commits under each member's own account, and peer review through pull requests when the final document is assembled [14]. This workflow also improves schedule control by exposing late work and integration problems earlier.

- Financial and Schedule Risk Analysis

| Risk | Type | Likelihood | Impact | Mitigation / response |
| --- | --- | --- | --- | --- |
| AI/API usage costs exceed the planning allowance. | Financial | Medium | Medium | Set usage limits, cache repeated tests, reduce test volume, and switch to a cheaper/local fallback if needed. |
| A selected cloud/database service requires a paid tier for a needed feature. | Financial | Low-Medium | Medium | Prototype locally first; verify limits before adoption; avoid vendor-specific features unless necessary. |
| Actual production maintenance costs are mistaken for prototype costs. | Financial | Medium | Medium | Keep prototype and production budgets separate; clearly label production items as future work. |
| Savings cannot be validated because procurement/repair data are unavailable. | Financial | High | Medium | Use formulas and approved sample data; label results as estimates and avoid claiming real savings without evidence. |
| Requirements or architecture change late. | Schedule | Medium | High | Freeze Must-Have scope after Phase 3; require team approval for changes that add major work. |
| Member availability drops because of other coursework or absence. | Schedule | Medium | High | Use shared documentation, small branches, cross-review, and internal deadlines so work can be reassigned. |
| Integration is postponed until the end of development. | Schedule | Medium | High | Merge small changes frequently and test combined workflows throughout the semester. |
| Data or AI service is not ready when testing begins. | Schedule / Financial | Medium | High | Prepare a synthetic dataset and fallback AI path early; keep deterministic baseline workflows working. |
| Testing and final submission compete for the same week. | Schedule | High | High | Set an internal feature freeze before the week of Nov 23 and reserve time specifically for fixes, documentation, and rehearsal. |

- Feasibility Finding

From the financial and schedule perspective, the academic prototype is feasible with conditions. Financial feasibility is strongest when the team uses existing devices, student/open-source tools, local development, a small demo environment, and strict AI/API usage controls. The project also has a credible benefit model because internal reuse can avoid new purchases, but actual savings must be calculated from real or approved sample procurement, transfer, and repair data rather than assumed as fact [11][12].

Schedule feasibility is acceptable if the three members work in parallel, freeze the Must-Have scope early, integrate continuously, and protect a buffer before the final testing/submission week. The largest schedule concern is the compressed end of the semester, where testing and final submission are both planned for the week of 23 November [12].

Accordingly, Member 2 recommends carrying the project forward on the financial and schedule dimensions provided that the team (1) maintains a low-cost prototype boundary, (2) monitors any paid AI/hosting usage, (3) controls scope after requirements are finalized, (4) prepares fallback data/AI options, and (5) sets internal deadlines earlier than the official lab deadlines. This is an analytical-area finding only; the final project-wide go / conditional go / no-go recommendation should be written jointly using evidence from all three members [14].

# References

[1] Khalifa University. (2026). Intelligent, AI-Powered Circular Campus Resource Exchange and Asset Life Cycle Management System: COSC 336 Fall 2026 project description.

[2] Khalifa University. (2026). COSC 336 Phase 2: Feasibility Study [Presentation slides].

[3] Group 9. (2026). Phase 1 Initial Plan and Requirement Gathering Document [Course submission].

[4] React. (n.d.). Quick Start. https://react.dev/learn

[5] FastAPI. (n.d.). First Steps. https://fastapi.tiangolo.com/tutorial/first-steps/

[6] PostgreSQL Global Development Group. (2026). Text Search Types. https://www.postgresql.org/docs/current/datatype-textsearch.html

[7] pgvector. (n.d.). Open-source vector similarity search for Postgres. https://github.com/pgvector/pgvector

[8] Sentence Transformers. (n.d.). Semantic Textual Similarity. https://sbert.net/docs/sentence_transformer/usage/semantic_textual_similarity.html

[9] Docker. (n.d.). Build and share a containerized application. https://docs.docker.com/get-started/tutorials/run-an-app/

[10] OWASP Foundation. (n.d.). Password Storage Cheat Sheet. https://cheatsheetseries.owasp.org/cheatsheets/Password_Storage_Cheat_Sheet.html

[11] Khalifa University, Department of Computer Science, Introduction to Software Engineering (COSC 336), “Intelligent, AI-Powered Circular Campus Resource Exchange and Asset Life Cycle Management System - Project Description,” Fall 2026.

[12] COSC 336 Project Team, “Phase 1 - Initial Plan and Requirement Gathering Document,” 13 September 2026.

[13] “Git, GitHub, and Copilot for Senior Design,” DOC-VC-01, Revision A, 2026.

[14] COSC 336 Phase 2 Feasibility Study Work-Allocation Guidance, course material provided to the project team, 2026.